Preparing a Proposal Budget: Lab

Class Workbook

Contents

Sponsor Budget Guidelines (NSF 18-581)	2

Activity 1: Interpret Sponsor Budget Guidelines/Requirements	2

Budget Scenario: Malaria Project with UK	3

Activity 2: Preparing the Budget	4

Header Information	4

Personnel Section	4

Let’s Practice! Calculate F&A Costs with Split Rates	4

Indirect/F&A Costs Section	4

Activity 3: Match the Budget and Budget Justification	5

Budget Justification 1	7

Budget Justification 2	7

Budget Justification 3	9

# Sponsor Budget Guidelines (NSF 18-581)

III. AWARD INFORMATION

Award size: Under this solicitation, the maximum total (for all years) award size is $2.5 million, including indirect costs. US-UK Collaborative Projects can request additional funding for the UK component of the project. The minimum award size is $1.5 million total project costs for all years, or $1.0 million for the US component of US-UK, US-Israel and US-China Collaborative Projects. For US-Israel Collaborative Projects, the maximum award size for the Israeli portion is $70,000/year. For US-China Collaborative Projects, the maximum award size for the Chinese portion is ¥4.5M total project costs for all years.

Award duration: The maximum award duration is five years.

RCN proposals: The maximum award size for RCN proposals is $500,000 as per the RCN solicitation. For US-UK Collaborative RCN proposals, the maximum award size for the US component is $500,000.

V. B. Budgetary Information

Cost Sharing:

Inclusion of voluntary committed cost sharing is prohibited.

Other Budgetary Limitations:

EEID projects must have a minimum budget of $1,500,000 in total project costs for all years; US-UK Collaborative, US-Israel, and US-China Collaborative projects must have a minimum budget of $1,000,000 in total project costs for all years. Research that falls within the scope of the EEID initiative but with project aims that do not require budgets of this magnitude should be directed to the appropriate core program.

Budget Preparation Instructions:

Subawards

In accordance with the applicable award terms and conditions, proposers are reminded of their responsibilities with regard to subawardees. Should an award be made, the primary awardee is responsible for ensuring compliance with the appropriate terms and conditions to, as well as the management and oversight of, any subawardees on the project, including any foreign subawardees.

## Activity 1: Interpret Sponsor Budget Guidelines/Requirements

| Question | Answer |
| --- | --- |
| 1. What is the maximum award duration? | Click or tap here to enter text. |
| 2. Is cost sharing allowed and/or required? | Click or tap here to enter text. |
| 3. What is the maximum budget size? | Click or tap here to enter text. |
| 4. What is the minimum award size? | - Total project costs for all years: Click or tap here to enter text. - US Component of US-UK Collaborative Projects: Click or tap here to enter text. - US Component of the US-Israel Collaborative Projects: Click or tap here to enter text. |

# Budget Scenario: Malaria Project with UK

Professor L.B. “Jeff” Jeffries from Chemistry has asked you to draft three-year budget for a proposal to the National Institutes of Health (NIH) International Research in Infectious Diseases (R01) Program. The proposal is due to NIH on July 18, 2026.

Professor Jeffries has provided the following information.

- The purpose of the project is to conduct basic research on malaria with collaborators in the UK. All of the work will be conducted on campus.

- The projected start date will be October 1, 2026, and the projected end date is September 30, 2029.

- Professor Jeffries will be the PI and will commit 20% effort on the proposed project during the academic year and 1 month during the summer. He is paid $131,000 per year and has an approved 2% merit increase before the start of the project.

  - Professor Jeffries has a 9-month academic year appointment.

  - Escalate his salary by 3% each project year.

- Co-PI Brinda Bakshi, who has an 11/12 appointment, will commit 0.5 months each project year and not work over the summer. She is paid $122,000 per year.

  - Escalate her salary by 4% each project year.

- Theresa Doyle, a post-doctoral researcher (post doc) will commit 50% effort on the proposed project and her current annual salary is $66,737.

  - Post-docs work on a calendar year schedule.

  - Escalate her salary by 3% each project year.

- A non-resident graduate student researcher (GSR) III will be hired and will begin working on the start date of the project. The GSR III will be attending classes full time during Winter, Spring, and Fall Quarters. The GSR will contribute 50% effort during the academic year on this project. The GSR will not be attending Summer Session, and will instead work on this project full-time. Current annual salary for a GSR III is $80,260.

  - Student fees should be escalated by 10% per AY.

- Fishers Scientific Bio-Tek Precision 2000 Automated Microplate Pipetting System (Catalog list price of $16,000) to be purchased in the first PY.

  - You have obtained a quote from Fisher Scientific (CA Company). For the purposes of this exercise, calculate an additional 20% of the catalog list price for shipping, handling and sales tax.

- Professor Jeffries’ will travel to meet with his collaborators in the UK twice each project year for an estimated total of $2,500 per trip.

  - Theresa Doyle will also attend one trip per year; same estimate total.

- Professor Jeffries’ will also attend a scientific conference in year 2 and again in year 3 to present on the research results. The conference will be in D.C. and his estimated trip cost is $1,500.

- Materials and Supplies:

  - Laboratory supplies: $1,500 each year

  - Computer dedicated to lab analysis for this project: $3,000 in year one

  - Purchase of a specific strain of malaria in year one: $2,000

  - Cattle supplies: $3,000 in year 1, $2000 in year 2 and $5,000 in year 3

- Publication Costs

  - $800 in years 2 and 3.

- Consultant: Charlie Apple is renowned cattle rancher and will serve as a consultant regarding the care and behavior of the cows to be studied. She will charge us $5,000 in each of the 3 years.

- The project will include a subaward to Stanford University in all years. Stanford University will receive $90,000 + 62% in F&A per year. Stanford will rely on our IRB all 3 years. This grant excludes F&A from the direct cost limit.

- We will also use the services of the Genome Center to perform data analysis on the genomes of non-infected and of infected cows. This will cost us $30,000 in each of the 3 years.

# Activity 2: Preparing the Budget

## Header Information

Open the Budget Spreadsheet for the class activity and enter the information from the Budget Scenario above (Project Start Date; Project End Date; NIH or non-NIH).

## Personnel Section

On the Budget Spreadsheet, enter the salary and effort for each person on the budget:

- Based on how effort information was provided to you, use the section that facilitates entering the information, either Person Months or %.

  - It is acceptable to enter AY info in one section (i.e., % section) and summer in another (i.e., Person Months section).

  - If an individual is committing different effort during the AY than during the summer, use a formula to enter the info.

    - Example: Co-PI Jones with a 9/12 appointment is committing 20% over the AY and 50% over 3 summer months. This can be reframed as 9 of 12 months at 20% plus 3 of 12 months at 50%. Formula: =(9*.2 +3*.5)/12

- Be sure to update the Appt. Type and Effort Type in each row to match the appointment.

- Add the Base Salary to each row.

  - If you want to escalate salary in the first project period, increase the Base Salary appropriately.

- Make sure Escalations are correct.

## Let’s Practice! Calculate F&A Costs with Split Rates

You are working on a budget for research project with a start date of September 1, 2023 and end date of August 31, 2024. The appropriate F&A Rate is 60% for FY 2023-24 and 61% for FY 2024-2025 with an MTDC Base. The MTDC is $300,000. What are the F&A Costs?

- Determine the months at the first rate. How many months occur before 6/30/2024?

Click or tap here to enter text.

- Calculate the F&A Costs at Rate 1.

($_____________ ÷ 12) × _____________ × _____________ = $_____________

- Determine number of month to charge at second rate. How many months occur on/after 7/1/2024?

Click or tap here to enter text.

- Calculate the F&A Costs at Rate 2.

($_____________ ÷ 12) × _____________ × _____________ = $_____________

- Calculate the F&A costs at both rates.

$_____________ + $_____________= $_____________

## Indirect/F&A Costs Section

On the Budget Spreadsheet:

Select the Indirect Cost Rate Type. If needed, reference UCD’s F&A and Fringe Benefit Rates

# Activity 3: Match the Budget and Budget Justification

Read the sample budget on the next page and the three budget justifications that follow it.

Select the matching budget justification below.

- Budget Justification 1	☐

- Budget Justification 2	☐

- Budget Justification 3	☐

Sample Budget

## Budget Justification 1

Senior Personnel

Margarat Jonas, PI (3.0 calendar months’ effort)

Dr. Jonas will serve as PI for the project, providing oversight, administration, and management of the project.

Sarah McMurphy, Co-PI (6.0 calendar months’ effort)

Dr. McMurphy will assist Dr. Jonas with oversight, administration, and management of the project.  She will serve as the main coordination hub for the project in both logistical planning and intellectual organization. Her responsibilities will include organizing meetings and trainings, leading recruiting efforts, oversee communication and development of web materials, and liaising with evaluator. She will also take part in curriculum development and teaching of the curriculum.

Timothy Chan, Co-PI (0.5 summer months’ effort)

Dr. Chan will take part in curriculum development and teaching the curriculum. He will assist in identifying, recruiting, and training additional faculty to teach the curriculum and take part in the Advisory Board and leadership team.

Susan Garcia, Academic Coordinator (3.0 calendar months’ effort)

Dr. Garcia will chair the Advisory Board and coordinate the involvement of faculty from STEM disciplines. She will provide feedback on curriculum design and delivery, as well as assisting the evaluator in collecting feedback from STEM faculty.

Fringe Benefits

Fringe benefits are calculated using UC Davis’s federally approved rates developed by UC Davis Costing and Policy, which are adjusted annually and calculated by title code and fiscal year.

Equipment

A dedicated server will be purchased in year 1 to store project data and the program’s website.  A dedicated service is necessary for data security and to ensure all features of the website are functional for collaboration.  Costs for the server are estimated at $6,200 based on web quotations from the university’s approved vendor.

Travel

Conference Travel: $1,500 is budgeted in years 2 through 5 to allow the PI or Co-PI to attend a relevant professional conference to disseminate information on the program and to collaborate.

Other Direct Costs

Materials and Supplies:

Supplies for trainers — $3,000 per year is budgeted for supplies for trainers.  Supplies will include mathematical design software licenses for modeling at $2,500 per year, and $500 per year for data storage and presentation materials.

Trainee research supplies - $6,500 in years 2 through 5 is budgeted for trainee research supplies to enable groups of trainees to undertake small research projects as a capstone to quarterly and year-long trainings.

## Budget Justification 2

Senior Personnel

Margarat Jonas, PI (1.5 academic months’ effort; 1.0 summer months’ effort)

Dr. Jonas will serve as PI for the project, providing oversight, administration, and management of the project. She will lead curriculum development, teach the curriculum, head the leadership team, and cooperate with evaluation. She will also lead efforts to coordinate among faculty on the advisory board and train additional faculty in curriculum implementation.

Sarah McMurphy, Co-PI (6.0 calendar months’ effort)

Dr. McMurphy will assist Dr. Jonas with oversight, administration, and management of the project.  She will serve as the main coordination hub for the project in both logistical planning and intellectual organization. Her responsibilities will include organizing meetings and trainings, leading recruiting efforts, oversee communication and development of web materials, and liaising with evaluator. She will also take part in curriculum development and teaching of the curriculum.

Timothy Chan, Co-PI (0.5 summer months’ effort)

Dr. Chan will take part in curriculum development and teaching the curriculum. He will assist in identifying, recruiting, and training additional faculty to teach the curriculum and take part in the Advisory Board and leadership team.

Susan Garcia, Academic Coordinator (3.0 calendar months’ effort)

Dr. Garcia will chair the Advisory Board and coordinate the involvement of faculty from STEM disciplines. She will provide feedback on curriculum design and delivery, as well as assisting the evaluator in collecting feedback from STEM faculty.

Postdoctoral Researcher (9.0 calendar months’ effort)

A postdoctoral researcher will work on the evaluation plan, create and administer surveys, and analyze the results and contribute to reporting.

Fringe Benefits

Fringe benefits are calculated using UC Davis’s federally approved rates developed by UC Davis Costing and Policy, which are adjusted annually and calculated by title code and fiscal year.

Equipment

A dedicated server will be purchased in year 1 to store project data and the program’s website.  A dedicated service is necessary for data security and to ensure all features of the website are functional for collaboration.  Costs for the server are estimated at $6,200 based on web quotations from the university’s approved vendor.

Travel

Conference Travel: $1,500 is budgeted in years 2 through 5 to allow the PI or Co-PI to attend a relevant professional conference to disseminate information on the program and to collaborate.

Other Direct Costs

Materials and Supplies:

Supplies for trainers — $3,000 per year is budgeted for supplies for trainers.  Supplies will include mathematical design software licenses for modeling at $2,500 per year, and $500 per year for data storage and presentation materials.

Trainee research supplies:  $6,500 in years 2 through 5 is budgeted for trainee research supplies to enable groups of trainees to undertake small research projects as a capstone to quarterly and year-long trainings.

Other:

MediaWorks Recharges for creation of online resources— $3,000 in year 1 and $1,000 in years 2 and 3 is budgeted for MediaWorks recharges ($91/hour) to create a website and online resources in support of the program.

Recruitment expenses— $600 in year 1 and $300 in years 2-5 is budgeted for trainee recruitment expenses including the creation and printing of recruitment flyers and meeting costs such as room rental, agenda creation, and online streaming fees.

Indirect Costs

Indirect Costs are calculated at UC Davis’s federally negotiated rate for instruction rate- 50% of Modified Total Direct Costs (MTDC).  Per NSF policy, participant support costs are excluded from the indirect cost base.

## Budget Justification 3

Senior Personnel

Margarat Jonas, PI (1.5 academic months’ effort; 1.0 summer months’ effort)

Dr. Jonas will serve as PI for the project, providing oversight, administration, and management of the project. She will lead curriculum development, teach the curriculum, head the leadership team, and cooperate with evaluation. She will also lead efforts to coordinate among faculty on the advisory board and train additional faculty in curriculum implementation.

Sarah McMurphy, Co-PI (6.0 calendar months’ effort)

Dr. McMurphy will assist Dr. Jonas with oversight, administration, and management of the project.  She will serve as the main coordination hub for the project in both logistical planning and intellectual organization. Her responsibilities will include organizing meetings and trainings, leading recruiting efforts, oversee communication and development of web materials, and liaising with evaluator. She will also take part in curriculum development and teaching of the curriculum.

Timothy Chan, Co-PI (0.5 summer months’ effort)

Dr. Chan will take part in curriculum development and teaching the curriculum. He will assist in identifying, recruiting, and training additional faculty to teach the curriculum and take part in the Advisory Board and leadership team.

Susan Garcia, Academic Coordinator (3.0 calendar months’ effort)

Dr. Garcia will chair the Advisory Board and coordinate the involvement of faculty from STEM disciplines. She will provide feedback on curriculum design and delivery, as well as assisting the evaluator in collecting feedback from STEM faculty.

Postdoctoral Researcher (9.0 calendar months’ effort)

A postdoctoral researcher will work on the evaluation plan, create and administer surveys, and analyze the results and contribute to reporting.

Fringe Benefits

Fringe benefits are calculated using UC Davis’s federally approved rates developed by UC Davis Costing and Policy, which are adjusted annually and calculated by title code and fiscal year.

Travel

Conference Travel: $1,500 is budgeted in years 2 through 5 to allow the PI or Co-PI to attend a relevant professional conference to disseminate information on the program and to collaborate.

Other Direct Costs

Materials and Supplies:

Server – A dedicated server will be purchased in year 1 to store project data and the program’s website.  A dedicated service is necessary for data security and to ensure all features of the website are functional for collaboration.  Costs for the server are estimated at $6,200 based on web quotations from the university’s approved vendor

Supplies for trainers — $3,000 per year is budgeted for supplies for trainers.  Supplies will include mathematical design software licenses for modeling at $2,500 per year, and $500 per year for data storage and presentation materials.

Trainee research supplies:  $6,500 in years 2 through 5 is budgeted for trainee research supplies to enable groups of trainees to undertake small research projects as a capstone to quarterly and year-long trainings.

Other:

Assessment/Evaluation Costs — $22,490 total over the 3 years of the project is budgeted for assessment and evaluation services.  Pricing is based on current quotations and includes focus group sessions, interviews, qualitative analysis and summaries, meeting attendance, and reports.

MediaWorks Recharges for creation of online resources— $3,000 in year 1 and $1,000 in years 2 and 3 is budgeted for MediaWorks recharges ($91/hour) to create a website and online resources in support of the program.

Recruitment expenses— $600 in year 1 and $300 in years 2-5 is budgeted for trainee recruitment expenses including the creation and printing of recruitment flyers and meeting costs such as room rental, agenda creation, and online streaming fees.

Indirect Costs

Indirect Costs are calculated at UC Davis’s federally negotiated rate for instruction rate- 50% of Modified Total Direct Costs (MTDC).  Per NSF policy, participant support costs are excluded from the indirect cost base.